## bp
Sr No | Approval of BPs | Approval stage | Time line targetted | Date of Submission | Date of Completion | Link for Documents | Documents required
1 | Application submission in o/o DTCP | RECORD | 2 WEEKS | - |  |  | •Scanned copy of approved zoning plan • BR-I • BR-II • 3 sets of complete building drawings showing area calculation and building services • Soft copy of all acad drawings compiled in a CD/DVD • BR-V(A1/A2) • Complete Structural Drawings • Empanelment of Structure Engineer, Proof Consultant and Geo Technical engineer • Receipt Scrutiny fee • Labour cess fee • NOC (AAI) • NOC regarding non utilisation of ground water
2 | Scrutiny of Documents by o/o DTCP | JD
PA
ATP
DTP
STP
3 | Letter forwarding circulation of BPs to DTP & STP(Circle), SE- HSVP, Fire officer-ULB, PKL and Observations letter issued | STP(HQ) |  |  |  |  | Circulation letter & Observation letter
4 | Examination by Concerned Circle - District Town Planner office | JD | 3 WEEKS
SD
PA
ATP
| Compilation of observations | DTP
5 | Examination by Concerned Circle - Senior Town Planner office | JD
ATP
| Compilation of observations | STP
| Site reports receival | [5 empty] | Field report issued
6 | Examination by SE / Executive Engineer - HSVP | JD |  |  |  |  | • Estate services layout • Slope calculation • Internal Services Layout • Toilet fixtures details • Water calculation • Storage tank details(underground/overhead) • Water treatment plant detail if any • STP capacity, design & calculation • Pump room details (Domestic/flushing/fire) • Sump-pump details.
SDM
HDM
CHD
SDE
CHD
SDO
XEN
SE
CE
| Compilation of observations | SE
| Site reports receival | [5 empty] | Field report issued
7 | Examination by Fire Officer, Urban Local Bodies | ASST. |  |  |  |  | Compliance of fire norms as per HBC/NBC Part IV
SUPDT.
CONSULTANT
| Compilation of observations | FIRE OFFICER
| Site reports receival | [5 empty] | Field report issued
8 | Compilation of Reports in o/o DTCP | JD | 1WEEK
PA
ATP
DTP
ARCHITECT
STP
ARCHITECT
CTP
DTP
9 | Fixing of Meeting of BPAC to review the comments / report of all above | STP
10 | Plan reviewed in BPAC Committee | o/o DTCP | 2 WEEKS
11 | Observations conveyed
12 | Resubmission of Dwgs after compliance
13 | Circulation of BPs to STP (circle)GGN, SE- HSVP, Fire officer-ULB, Pkl for signatures. |  | 3 WEEKS
14 | Examination of BPs at Field offices
15 | Compilation of Reports in o/o DTCP | JD | 2 WEEKS
16 | Verification of the Licence / CLU permission / pending dues by the Department | SO
AO
CAO
17 | Approved Building Plans & BR-III issued | JD
ATP
DTP
ARCHITECT
STP
CTP